## General Check list
| Monday | Start planning the test cases for the next release
| Monday | Create test cycle in Jira
| Monday | Tell broker API if there are API tickets | Laura Castillo
| Monday | Send a Message to Tracy Brown to ask her to test a policy.
| Thursday | Set the meeting for the Demo with the tickets that will be checked | AP (Grant Trutman)/ BMT(tracy brown)/Davis Tominaga
| Friday | Demo | If Grant can not go, then invite Amy Landefeld
| Friday | Send and email for approval
| Friday | Once you have the approval, go to release a close the ticket
| Friday | Fill out the ckeck list / Write what tests have been DEMo and to whom
| Friday | 4:00 pm (EST) send a Sign off email
UAT- Test evidence attached to the Test Cases. (xxxxxxxxxxxxxxx) provided the sign-off via email for todays UAT-PROD release xxxxxxxx
UAT - Tested and ready to go to Prod on Oct-14-2022. Test evidence attached to the test cases. Tracey Brown Davis Tominaga and Grant Troutman provided Sign-off via email.
Import Test Cases to Jira
Go to Zephys Squad/ Cycle Summary
Select example: DRC 22-July-2022
Create/Select the UAT release (UAT July12 / July 15)
On the left click on Import Test Cases
Choose the file you want to upload.
Click on (Use Configuration File) if you don’t want to do this manually
Next
Row Number to begin to import = 2
Discriminator=ID change
Import all sheets
Next
Map each field to the corresponding in the excell file
Next
Validate
This is only onece: Save the configuration for future use to be used as the "Configuartion File"
Begin Import
Filters
Advance Issue Search
Proyect=Beazley Digital; Type=Test; More=Created Date/within 10 minutes
Save as= name it the way you want
Submit
After the import, we need to Add the test cases
Go to Zephyr Squad
Cycle Summary
Select the UAT cycle which I want to add the ticktes to
On the rigth top next to Columns select Add Tests
Via Search Filter
Select the filter name you just saved/Select Assigneed to Emiliano Duque
Add

## Prod-Dec-05-2022
Type | ID | Summary | Write-TC | Test Status | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-14861 | BMT - ASAP - Update 2023 Lloyd's Security Schedule with new 2023 wording from Compliance - Non-Admitted Effective 1/1/2023 | x | ok | x | x | x
| BD-14870 | BBR - ASAP - Update 2023 Lloyd's Security Schedule with new 2023 wording from Compliance - Non-Admitted Effective 1/1/2023 | x | ok | x | x | x
DEMO
Type | ID | Summary
| BD-14861 | BMT - ASAP - Update 2023 Lloyd's Security Schedule with new 2023 wording from Compliance - Non-Admitted Effective 1/1/2023
| BD-14870 | BBR - ASAP - Update 2023 Lloyd's Security Schedule with new 2023 wording from Compliance - Non-Admitted Effective 1/1/2023
[9 empty] | Test case | Policy number
[8 empty] | BD-2405 | TC 1 | VG00004524AA
[8 empty] | BD-2406 | TC 2 | WG00004525AA
[8 empty] | BD-2409 | TC 3 | VG00004526AA
[8 empty] | BD-2411 | TC 4 | VG00004527AA
[8 empty] | BD-2412 | TC 5 | WG00004528AA
[8 empty] | BD-2415 | TC 6 | VG00004529AA
[8 empty] | BD-2416 | TC 7 | VG00004530AA
[8 empty] | BD-2417 | TC 8 | VG00004538AA
[8 empty] | BD-2418 | TC 9 | VG00004539AA
[8 empty] | BD-2419 | TC 10 | VG00004543AA
[8 empty] | BD-2420 | TC 11 | VG00004533AA
[8 empty] | BD-2421 | TC 12 | VG00004532AA
[8 empty] | BD-2422 | TC 13 | VG00004534AA
[8 empty] | BD-4936 | TC 14 | VG00004537AA
[8 empty] | BD-4937 | TC 15 | VG00004544AA
[8 empty] | BD-4938 | TC 16 | VG00004541AA

## Prod-Nov-28-2022
Type | ID | Summary | Write-TC | Test Status | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-12879 | BBR - Update Standard SLDFs - Effective 11-29-2022
DEMO
Type | ID | Summary
| BD-12879 | BBR - Update Standard SLDFs - Effective 11-29-2022
[9 empty] | Test case | Policy number
[8 empty] | BD-2405 | TC 1 | VG00004488AA
[8 empty] | BD-2406 | TC 2 | WG00004489AA
[8 empty] | BD-2409 | TC 3 | VG00004490AA
[8 empty] | BD-2411 | TC 4 | VG00004491AA
[8 empty] | BD-2412 | TC 5 | WG00004492AA
[8 empty] | BD-2415 | TC 6 | VG00004493AA
[8 empty] | BD-2416 | TC 7 | VG00004494AA
[8 empty] | BD-2417 | TC 8 | VG00004495AA
[8 empty] | BD-2418 | TC 9 | VG00004501AA
[8 empty] | BD-2419 | TC 10 | VG00004503AA
[8 empty] | BD-2420 | TC 11 | VG00004496AA
[8 empty] | BD-2421 | TC 12 | VG00004497AA
[8 empty] | BD-2422 | TC 13 | VG00004498AA
[8 empty] | BD-4936 | TC 14 | VG00004499AA
[8 empty] | BD-4937 | TC 15 | VG00004504AA
[8 empty] | BD-4938 | TC 16 | VG00004502AA

## Prod-Nov-23-2022
Type | ID | Summary | Write-TC | Test Status | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-13892 | BMT-1/1/23-War and Cyber War Exclusion Endst - additional Admitted states to be added. | x | ok | x | x
| BD-13924 | BMT-1/1/23-Infrastructure Failure Exclusion Amendatory Endst- additional Admitted states to be added. | x | ok | x | x
| BD-13935 | BBR-1/1/23-First Party Loss Exclusions Amendatory Endst - additional Admitted states to be added. | x | ok | x | x
D | BD-14061 | BBR-1/1/23-Catastrophic First Party Loss Amendatory Endst - additional Admitted states to be added. | x | ok | x | x
D | BD-14062 | BBR-1/1/23- War and Cyber War Exclusion Endst - additional Admitted states to be added. | x | ok | x | x
| BD-12873 | BMT/GL - ASAP - Update UMR/Authority Reference Number on Dec Page F00730 022019 and F00742 022019 for all Non-Admitted risks with effective date on or after 1/1/23. | x | ok | x | x
| BD-12875 | BBR, BMT/GL, MT - 1/1/23 - Replace Jennifer Englund's signature with Vanessa Ortega's | x | ok | x | x
DEMO
Type | ID | Summary
x | BD-13892 | BMT-1/1/23-War and Cyber War Exclusion Endst - additional Admitted states to be added.
x | BD-13924 | BMT-1/1/23-Infrastructure Failure Exclusion Amendatory Endst- additional Admitted states to be added.
x | BD-13935 | BBR-1/1/23-First Party Loss Exclusions Amendatory Endst - additional Admitted states to be added.
x | BD-14061 | BBR-1/1/23-Catastrophic First Party Loss Amendatory Endst - additional Admitted states to be added.
x | BD-14062 | BBR-1/1/23- War and Cyber War Exclusion Endst - additional Admitted states to be added.
x | BD-12873 | BMT/GL - ASAP - Update UMR/Authority Reference Number on Dec Page F00730 022019 and F00742 022019 for all Non-Admitted risks with effective date on or after 1/1/23.
x | BD-12875 | BBR, BMT/GL, MT - 1/1/23 - Replace Jennifer Englund's signature with Vanessa Ortega's
[9 empty] | Test case | Policy number
[8 empty] | BD-2405 | TC 1 | VG00004445AA
[8 empty] | BD-2406 | TC 2 | WG00004446AA
[8 empty] | BD-2409 | TC 3 | VG00004447AA
[8 empty] | BD-2411 | TC 4 | VG00004448AA
[8 empty] | BD-2412 | TC 5 | WG00004449AA
[8 empty] | BD-2415 | TC 6 | VG00004450AA
[8 empty] | BD-2416 | TC 7 | VG00004451AA
[8 empty] | BD-2417 | TC 8 | VG00004481AA
[8 empty] | BD-2418 | TC 9 | VG00004482AA
[8 empty] | BD-2419 | TC 10 | VG00004480AA
[8 empty] | BD-2420 | TC 11 | VG00004452AA
[8 empty] | BD-2421 | TC 12 | VG00004453AA
[8 empty] | BD-2422 | TC 13 | VG00004454AA
[8 empty] | BD-4936 | TC 14 | VG00004455AA
[8 empty] | BD-4937 | TC 15 | VG00004479AA
[8 empty] | BD-4938 | TC 16 | VG00004483AA

## Prod-Nov-11-2022
Type | ID | Summary | Write-TC | Status | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-11648 | BBR - AP/UWP -Apply $25k to new separate Retentions for unfavorable answers to Ransomware Questions 6A,7A,11,12, or 12A. | x | ok | x | x
| BD-5111 | UWP - BMT- update to GL standard endts | x | ok | x | x
| BD-13375 | BBR AP/UWP - Update Rater for MM Auto dealership over $233,333,333 revenue band - Eliminate Quote Option Limit 4 - Retention related values not applicable | x | ok | x | x
| BD-13036 | QA/AP-In the quote letter is not showing up the First Party Retention, when the user trigger the 12A question unfavorably | x | ok | x | x
D | BD-11918 | BMT-1/1/23-War and Cyber War Exclusion Endst | x
D | BD-11919 | BMT-1/1/23-Infrastructure Failure Exclusion Amendatory Endst | x
| BD-11922 | BBR-1/1/23-First Party Loss Exclusions Amendatory Endst | x | ok | x | x
| BD-11923 | BBR-1/1/23-Catastrophic First Party Loss Amendatory Endst | x | ok | x | x
D | BD-12868 | BBR-1/1/23- War and Cyber War Exclusion Endst | x
D | BD-12874 | BMT - ASAP - Add 2023 Lloyd's Security Endorsement & Retire 2022 version - Non-Admitted Effective 1/1/2023 | x
D | BD-12877 | BBR - ASAP - Add 2023 Lloyd's Security Endorsement & Retire 2022 version - Non-Admitted Effective 1/1/2023 | x
| BD-13657 | UAT - BBR - AP- Does not apply $25k to new separate Retentions for unfavorable answers to Ransomware Questions 6A,7A,11,12, or 12A, when Revenue is les than 2M. | x | ok | x | x | x
D | BD-13933 | QA-AP- The form War and Cyber War Exclusion End is not showing up in the quote letter for BBR quotes | x
DEMO
Type | ID | Summary
x | BD-11648 | BBR - AP/UWP -Apply $25k to new separate Retentions for unfavorable answers to Ransomware Questions 6A,7A,11,12, or 12A.
x | BD-5111 | UWP - BMT- update to GL standard endts
x | BD-13375 | BBR AP/UWP - Update Rater for MM Auto dealership over $233,333,333 revenue band - Eliminate Quote Option Limit 4 - Retention related values not applicable
x | BD-11918 | BMT-1/1/23-War and Cyber War Exclusion Endst
x | BD-11919 | BMT-1/1/23-Infrastructure Failure Exclusion Amendatory Endst
x | BD-11922 | BBR-1/1/23-First Party Loss Exclusions Amendatory Endst
x | BD-11923 | BBR-1/1/23-Catastrophic First Party Loss Amendatory Endst
x | BD-12868 | BBR-1/1/23- War and Cyber War Exclusion Endst
x | BD-12874 | BMT - ASAP - Add 2023 Lloyd's Security Endorsement & Retire 2022 version - Non-Admitted Effective 1/1/2023
x | BD-12877 | BBR - ASAP - Add 2023 Lloyd's Security Endorsement & Retire 2022 version - Non-Admitted Effective 1/1/2023
[9 empty] | Test case | Policy number
[8 empty] | BD-2405 | TC 1 | VG00004409AA
[8 empty] | BD-2406 | TC 2 | WG00004410AA
|  | BD-11648 | [5 empty] | BD-2409 | TC 3 | VG00004411AA
|  | $25.000 RSA Rule | [5 empty] | BD-2411 | TC 4 | VG00004437AA
|  | ECR = Each Claim Retention | [5 empty] | BD-2412 | TC 5 | WG00004439AA
[8 empty] | BD-2415 | TC 6 | VG00004412AA
[8 empty] | BD-2416 | TC 7 | VG00004413AA
[8 empty] | BD-2417 | TC 8 | VG00004432AA
[8 empty] | BD-2418 | TC 9 | VG00004423AA
[8 empty] | BD-2419 | TC 10 | VG00004422AA
[8 empty] | BD-2420 | TC 11 | VG00004441AA
[8 empty] | BD-2421 | TC 12 | VG00004415AA
[8 empty] | BD-2422 | TC 13 | VG00004419AA
[8 empty] | BD-4936 | TC 14 | VG00004424AA
[8 empty] | BD-4937 | TC 15 | VG00004442AA
[8 empty] | BD-4938 | TC 16 | VG00004435AA
ALL (6a, 7a, 11, 12 or 12a) = Favorably OR ECR >= $25.000
First Party Sublimits = $25.000
The values are shown in the quote document.
First Party Sublimits = ECR The values are NOT shown in the quote document.
First Party Sublimits = ECR The values are shown in the quote document.
NO
YES
ECR >= $25000
NO
YES

## Prod-Nov-04-2022
Type | ID | Summary | Write-TC | Status | Test/ Attach evidence TC Level | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email |  | Test case | Policy number
| BD-11648 | BBR - AP/UWP -Apply $25k to new separate Retentions for unfavorable answers to Ransomware Questions 6A,7A,11,12, or 12A. | x | ok |  |  |  |  | BD-2405 | TC 1
| BD-11919 | BMT-1/1/23-Infrastructure Failure Exclusion Amendatory Endst | [6 empty] | BD-2406 | TC 2
| BD-5111 | UWP - BMT- update to GL standard endts | x | ok |  |  |  |  | BD-2409 | TC 3
| BD-13375 | BBR AP/UWP - Update Rater for MM Auto dealership over $233,333,333 revenue band - Eliminate Quote Option Limit 4 - Retention related values not applicable | x | ok |  |  |  |  | BD-2411 | TC 4
| BD-13036 | QA/AP-In the quote letter is not showing up the First Party Retention, when the user trigger the 12A question unfavorably | x | ok |  |  |  |  | BD-2412 | TC 5
[9 empty] | BD-2415 | TC 6
[9 empty] | BD-2416 | TC 7
[9 empty] | BD-2417 | TC 8
[9 empty] | BD-2418 | TC 9
[9 empty] | BD-2419 | TC 10
[9 empty] | BD-2420 | TC 11
|  | Note: This release was canceled. | [6 empty] | BD-2421 | TC 12
[9 empty] | BD-2422 | TC 13
[9 empty] | BD-4936 | TC 14
[9 empty] | BD-4937 | TC 15
[9 empty] | BD-4938 | TC 16
DEMO
Type | ID | Summary
| BD-11648 | BBR - AP/UWP -Apply $25k to new separate Retentions for unfavorable answers to Ransomware Questions 6A,7A,11,12, or 12A.
| BD-11919 | BMT-1/1/23-Infrastructure Failure Exclusion Amendatory Endst
| BD-5111 | UWP - BMT- update to GL standard endts
| BD-13375 | BBR AP/UWP - Update Rater for MM Auto dealership over $233,333,333 revenue band - Eliminate Quote Option Limit 4 - Retention related values not applicable
IMPORTANT! Erin Henne Jessie Du Daniel Rodrigues - We have been working on this all day. We are having issues with the deployments and it just doesn't look possible to go to UAT today. Emiliano Duque, Keanu Freitas, Durga Gannu(Associate) (Guest), and the rest of the team discussed a strategy for moving forward. Our plan is to push to QA today, whatever it takes, and schedule a UAT deployment for tomorrow. This means that we will have to cancel Prod deployment for tomorrow, 11/4. We would resume the normal cadence for next week: Tue, 11/8 > UAT and Fri, 11/11 > Prod. Devs are still making progress on the end of year updates and that hasn't slowed down. We are still on track to deliver all end of year updates before Thanksgiving. (We would discuss next week how we would like to adjust the last sprint in November to account for Thanksgiving)
$25.000 RSA Rule
ALL (6a, 7a, 11, 12 or 12a) = Favorably OR ECR >= $25.000
First Party Sublimits = $25.000
The values are shown in the quote document.
First Party Sublimits = ECR The values are NOT shown in the quote document.
First Party Sublimits = ECR This is reflected in the document
NO
YES
YES
At least one(6a, 7a, 11, 12 or 12a) = Unavorably
YES
ECR >= $25000
NO
YES

## Prod-Oct-21-2022
Type | ID | Summary | Write-TC | Status | Test/ Attach evidence TC Level | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email |  | Test case | Policy number
| BD-10956 | BMT-Amend Definition of Professional Services - Add state CA | [6 empty] | BD-2405 | TC 1 | VG00004350AA
| BD-5059 | UWP BMT - Automatically attach Ransomware Application F00765 082020 to all BMT Renewal Quotes | [6 empty] | BD-2406 | TC 2 | WG00004351AA
[9 empty] | BD-2409 | TC 3 | VG00004352AA
[9 empty] | BD-2411 | TC 4 | VG00004353AA
[9 empty] | BD-2412 | TC 5 | WG00004354AA
[9 empty] | BD-2415 | TC 6 | VG00004355AA
[9 empty] | BD-2416 | TC 7 | VG00004356AA
[9 empty] | BD-2417 | TC 8 | VG00004359AA
[9 empty] | BD-2418 | TC 9 | VG00004365AA
[9 empty] | BD-2419 | TC 10 | VG00004366AA
[9 empty] | BD-2420 | TC 11 | VG00004360AA
[9 empty] | BD-2421 | TC 12 | VG00004361AA
[9 empty] | BD-2422 | TC 13 | VG00004364AA
[9 empty] | BD-4936 | TC 14 | VG00004363AA
[9 empty] | BD-4937 | TC 15 | VG00004368AA
[9 empty] | BD-4938 | TC 16 | VG00004367AA
DEMO
Type | ID | Summary
| BD-10956 | BMT-Amend Definition of Professional Services - Add state CA
| BD-5059 | UWP BMT - Automatically attach Ransomware Application F00765 082020 to all BMT Renewal Quotes

## Prod-Oct-14-2022
Type | ID | Summary | Write-TC | Status | Test/ Attach evidence TC Level | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-11129 | BBR/BMT - AP/UWP- Add a new mandatory field 'Total Employee Count' for TRIA data reporting | [6 empty] | BD-2405 | VG00004276AA | TC 1 | VG00004326AA
| BD-11989 | BBR - AP/UWP -When RSA Question #7 is answered 'No' do not trigger the First Party Sublimit rule | [6 empty] | BD-2406 | WG00004277AA | TC 2 | WG00004327AA
[9 empty] | BD-2409 | VG00004297AA | TC 3 | VG00004328AA
[9 empty] | BD-2411 | VG00004298AA | TC 4 | VG00004329AA
[9 empty] | BD-2412 | WG00004283AA | TC 5 | WG00004330AA
[9 empty] | BD-2415 | VG00004284AA | TC 6 | VG00004331AA
[9 empty] | BD-2416 | VG00004285AA | TC 7 | VG00004332AA
[9 empty] | BD-2417 | VG00004304AA | TC 8 | VG00004333AA
[9 empty] | BD-2418 | VG00004305AA | TC 9 | VG00004340AA
[9 empty] | BD-2419 | VG00004299AA | TC 10 | VG00004341AA
[9 empty] | BD-2420 | VG00004291AA | TC 11 | VG00004334AA
[9 empty] | BD-2421 | VG00004292AA | TC 12 | VG00004335AA
[9 empty] | BD-2422 | VG00004293AA | TC 13 | VG00004336AA
[9 empty] | BD-4936 | VG00004301AA | TC 14 | VG00004337AA
[9 empty] | BD-4937 | VG00004314AA | TC 15 | VG00004342AA
[9 empty] | BD-4938 | VG00004313AA | TC 16 | VG00004339AA
DEMO
Type | ID | Summary
| BD-11129 | BBR/BMT - AP/UWP- Add a new mandatory field 'Total Employee Count' for TRIA data reporting
| BD-11989 | BBR - AP/UWP -When RSA Question #7 is answered 'No' do not trigger the First Party Sublimit rule

## Prod-Oct-07-2022
Type | ID | Summary | Write-TC | Status | Test/ Attach evidence TC Level | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email |  | Test case | Policy number
| BD-10382 | BBR - MA to be made available for Admitted | x |  | x | x | x |  | BD-2405 | TC 1 | VG00004276AA | Hi Emiliano,
| BD-10902 | BBR -MT to be made available for Admitted | x |  | x | x | x |  | BD-2406 | TC 2 | WG00004277AA
| BD-7967 | AP/UWP -Introduce Admitted BBR App for MA Insureds, Update Surplus App | x |  | x | x | x |  | BD-2409 | TC 3 | VG00004297AA | Please find below policy numbers for the test cases, below are the observations:
| BD-11703 | AP BBR - Update Bind Instructions on the Quote Options Screen - add turquoise coloring | x |  | x | x | x |  | BD-2411 | TC 4 | VG00004298AA
| BD-10675 | Make sure the Licensed Broker ID is on the json and the Licensed Broker ID is used downstream for Reporting rather than Submitting Broker ID | [6 empty] | BD-2412 | TC 5 | WG00004283AA | 1. NJ tax limit is changed from 0.6% to 0.5% and same is updated in scripts for validation
[9 empty] | BD-2415 | TC 6 | VG00004284AA | 2. For address change from CA to NY - the state, city and zip code is not updated in LES (VG00004313AA)
[9 empty] | BD-2416 | TC 7 | VG00004285AA
[9 empty] | BD-2417 | TC 8 | VG00004304AA
[9 empty] | BD-2418 | TC 9 | VG00004305AA
| DEMO | [7 empty] | BD-2419 | TC 10 | VG00004299AA
Type | ID | Summary | [6 empty] | BD-2420 | TC 11 | VG00004291AA
| BD-10382 | BBR - MA to be made available for Admitted | [6 empty] | BD-2421 | TC 12 | VG00004292AA
| BD-10902 | BBR -MT to be made available for Admitted | [6 empty] | BD-2422 | TC 13 | VG00004293AA
| BD-7967 | AP/UWP -Introduce Admitted BBR App for MA Insureds, Update Surplus App | [6 empty] | BD-4936 | TC 14 | VG00004301AA
| BD-11703 | AP BBR - Update Bind Instructions on the Quote Options Screen - add turquoise coloring | [6 empty] | BD-4937 | TC 15 | VG00004314AA
[9 empty] | BD-4938 | TC 16 | VG00004313AA

## Sep Successes
Success Item | No. of Releases | No. of U.S. Tested | No. of Defects Tested | Comments
DRC Sep 9th | 1 | 6 | 0 | 25 Test Cases tested
DRC Sep 16th | 1 | 2 | 0 | 11 Test Cases tested
DCR Sep 29th | 1 | 2 | 0 | 21 Test Cases tested

## Prod-Sep-29-2022
Type | ID | Summary | Write-TC | Status | Test/ Attach evidence TC Level | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-10302 | AP/UWP-New Colors and Logo - Effective 9/29 | x | pass | x
| BD-11649 | AP BBR - Update Bind Instructions on the Quote Options Screen - effective 9/28 | x | pass | x
Blockers or Importatnt tickets for the release
Tickets added during the week
DEMO
Type | ID | Summary
| BD-10302 | AP/UWP-New Colors and Logo - Effective 9/29
| BD-11649 | AP BBR - Update Bind Instructions on the Quote Options Screen - effective 9/28

## Prod-Sep-16-2022
Type | ID | Summary | Write-TC | Status | Test/ Attach evidence TC Level | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-9725 | AP/UWP- For RSA questions 11, 12 and 12A, remove knockout and apply sublimit logic based on Revenue | x |  | x | x | x
| BD-10967 | QA-UWP- When the user selects the blank space from the dropdown agent of service field , they can go to the next page . | x |  | x | x | x
Blockers or Importatnt tickets for the release
Tickets added during the week
DEMO
Type | ID | Summary
| BD-9725 | AP/UWP- For RSA questions 11, 12 and 12A, remove knockout and apply sublimit logic based on Revenue
| BD-10967 | QA-UWP- When the user selects the blank space from the dropdown agent of service field , they can go to the next page .

## Prod-Sep-09-2022
Type | ID | Summary | Write-TC | Status | Test/ Attach evidence TC Level | Attach evidence Defect Level | All TC DONE | Close BD Sign-off email
| BD-5110 | BMT - UWP - update to quote email | x |  | x | x | x
| BD-9763 | BMT-Amend Definition of Professional Services, addt states approved | x |  | x | x | x
| BD-9764 | BMT and BBR -Remove 'Foley & Lardner LLP' as Service of Suit option for all states | x |  | x | x | x
| BD-9765 | BMT-Joint Venture Endorsement | x |  | x | x | x
| BD-9766 | BMT-Amend Definition of Professional Services | x |  | x | x | x
| BD-9927 | BMT-Territorial Exclusion Endorsement | x |  | x | x | x
Blockers or Importatnt tickets for the release
Tickets added during the week
DEMO
Type | ID | Summary
| BD-5110 | BMT - UWP - update to quote email
| BD-9763 | BMT-Amend Definition of Professional Services, addt states approved
| BD-9764 | BMT and BBR -Remove 'Foley & Lardner LLP' as Service of Suit option for all states
| BD-9765 | BMT-Joint Venture Endorsement
| BD-9766 | BMT-Amend Definition of Professional Services
| BD-9927 | BMT-Territorial Exclusion Endorsement

## Aug Successes
Success Item | No. of Releases | No. of U.S. Tested | No. of Defects Tested | Comments
DRC Aug 5th | 1 | 3 | 3 | 15 Test Cases tested
DRC Aug 12th | 1 | 1 | 2 | 10 Test Cases tested
DCR Sep 1st | 1 | 2 | 4 | 27 Test Cases tested

## Prod-Aug-26-Sep-12022
Type | ID | Summary | Creat TC US | Test/ Attach evidence TC Level | Attach evidence Defect Level | Status | Close TC | Close with Sign-off email
Story | BD-7856 | NJ Assessment Reduction - Effective 10/1/2022 or later for Admitted Policies and Quotes in NJ. | x | x | x |  | x | x
Story | BD-9466 | AP-Elementary/High School Industry Class updated to Surplus | x | x | x |  | x | x
Defect | BD-9144 | AP - Broker is getting an error message when using "Investment Advise" as Industry Class - Hazard group selection is not valid | x | x | x |  | x | x
Defect | BD-9388 | Endorsement Configuration | x | x | x |  | x | x
Defect | BD-9926 | BBR-AP UI - Retail Business industry class, is Allowed but was Declined in DRC - No pricings | x | x | x |  | x | n
Defect | BD-10125 | BBR-UAT- Industry Class gets empty after hitting Submit for Clearance button | x | n | n |  | x | n
Blockers or Importatnt tickets for the release
Tickets added during the week
DEMO
Type | ID | Summary
Story | BD-7856 | NJ Assessment Reduction - Effective 10/1/2022 or later for Admitted Policies and Quotes in NJ.
Story | BD-9466 | AP-Elementary/High School Industry Class updated to Surplus
Defect | BD-9144 | AP - Broker is getting an error message when using "Investment Advise" as Industry Class - Hazard group selection is not valid
Defect | BD-9388 | Endorsement Configuration

## Prod-Aug-12-2022
Type | ID | Summary | Creat TC US | Test/ Attach evidence TC Level | Attach evidence Defect Level | Status | Close TC | Close with Sign-off email
User Story | BD-9088 | BMT-Music Copyright Claims Exclusion endorsement | x | x | x |  | x
Defect | BD-9596 | AP - Broker is getting an error message "Action Required: Construction contractors and related services not in list" |  | x | x |  | x
Defect | BD-9275 | PROD- Out of sequence endorsement message is displayed on a RNW Policy without previous amendments |  | x |  |  | x
Blockers or Importatnt tickets for the release
Tickets added during the week
DEMO
Type | ID | Summary
User Story | BD-9088 | BMT-Music Copyright Claims Exclusion endorsement
Defect | BD-9596 | AP - Broker is getting an error message "Action Required: Construction contractors and related services not in list"

## Prod-Aug-05-2022
Type | ID | Summary | Creat TC US | Test/ Attach evidence TC Level | Attach evidence Defect Level | Status | Close TC | Close with Sign-off email
Story | BD-9273 | AP-Incorrect 1st Party Sublimits | x | x | x | Ready to move to prod | x
Story | BD-7852 | Renewal Solicitations Not Including Ransomware Supplemental | x | x |  | Ready to move to prod | x
Story | BD-8973 | AP - BBR - Default Select Sub-limits to $1M When MFA Questions Are Answered 'No' for MM - with Revenue > $35M | x
Defect | BD-7518 | Admin - Valid email can´t be assigned to a user |  | x | x | Ready to move to prod | x
Defect | BD-8984 | ADO 22788 - Output Additional Data format issue in endorsement list section for the form E12229 062022 |  | x | x | Ready to move to prod | x
Defect | BD-9102 | UAT - BMT - Update Lloyds service of suit in CA when it is created from Insight |  | x | x | Ready to move to prod | x
Blockers or Importatnt tickets for the release
Tickets added during the week
DEMO
Type | ID | Summary
Story | BD-9273 | AP-Incorrect 1st Party Sublimits
Story | BD-7852 | Renewal Solicitations Not Including Ransomware Supplemental
Story | BD-8973 | AP - BBR - Default Select Sub-limits to $1M When MFA Questions Are Answered 'No' for MM - with Revenue > $35M

## Prod-July-22-2022
Type | ID | Summary | Test Cases | Attach evidence TC Level | Attach evidence Issue Level | Status | Close TC | Close with Sign-off email
Story | BD-4387 | BZ Merge : SL - BBR - AP : Remove / Hide the "New Quote" button from the Quotes tab inside Customers tab. | x | x | x | Ready to move to PROD | x | x
Story | BD-7616 | BMT-New Endo - E12229 062022 ed. - Amend Definition of Professional Services | x | x | x | Ready to move to PROD | x | x
Story | BD-8063 | BBR - Do not send a Record to Insight for Declination Status and Reasons - Insight not setup to receive records | x | x | x | Ready to move to PROD | x | No Demo
Story | BD-8524 | BBR - AP - Display Underwriter Referral and Request Help Submissions - Created by Field | x | x | x | Ready to move to PROD | x | x
Defect | BD-8033 | Admin - Agency name validation prevents me from updating it |  |  |  | Ready to move to PROD |  |  | This was tested by Jessie
Defect | BD-8172 | UAT - BMT - Update Lloyds service of suit in CA |  |  |  | Ready to move to PROD |  |  | One new defect (BD-9102) was created related to the scenario 1 of this ticket.
Blockers or Importatnt tickets for the release
Tickets added during the week
DEMO
Type | ID | Summary
Story | BD-4387 | BZ Merge : SL - BBR - AP : Remove / Hide the "New Quote" button from the Quotes tab inside Customers tab.
Story | BD-7616 | BMT-New Endo - E12229 062022 ed. - Amend Definition of Professional Services
Story | BD-8524 | BBR - AP - Display Underwriter Referral and Request Help Submissions - Created by Field |  |  |  | Q# 2029631

## Prod-July-15-2022
Type | ID | Summary | Test Cases | Status
Story | BD-7611 | BBR-RPS Auto Program to default to Surplus | x | Ready to move to PROD
Story | BD-7614 | Add debits based on answers to RSA questions for all business to the Privacy & Security Controls Procedures | x | All the negative RSA re-tested ok, but 13B=NO is not rating.
Story | BD-7379 | BMT - retire/replace OR amendatory endt | x | Ready to move to PROD
Story | BD-2530 | BBR - AP - Display Underwriter Referral and Request Help Submissions | x | Ready to move to PROD
Defect | BD-7898 | PROD - AP - Submission cleared on Insight remains submitted on myBeazley
Defect | BD-8073 | PROD-AP-Quote Letter and Application not producing
Defect | BD-7177 | PROD - GC Attachments Won't Upload due to special characters |  | Ready to move to PROD
Defect | BD-8621 | QA - BBR - Rating edit appears when revenue entered is >$35m for Auto Dealership
Blockers or Importatnt tickets for the release
Tickets added during the week
BD-7943 | UAT/QA-UWP-The field "Named Insured" appears empty from the Renewall Questionnaire document
BD-8172 |  | UAT - BMT - Update Lloyds service of suit in CA
BD-8949 |  | I MUST TALK TO DANNY ABOUT IT
DEMO
Type | ID | Summary
Story | BD-7611 | BBR-RPS Auto Program to default to Surplus
Story | BD-7614 | Add debits based on answers to RSA questions for all business to the Privacy & Security Controls Procedures
Story | BD-7379 | BMT - retire/replace OR amendatory endt
Story | BD-2530 | BBR - AP - Display Underwriter Referral and Request Help Submissions

## Prod-July-1-2022
Bugs
# | ID (BD-) | Evidence Actual Result | Test Cases | Status done? | Notes
| 7392 |  | x | x | It was tested previously by Loren. | DEMO
| 7206 |  |  |  | As soon as I got the UAT build, I'll check it | ID | Summary | Issue Type | Status | Test Data
[6 empty] | BD-7205 | BMT/BBR - update lloyds service of suit in CA | Stoy | UAT | BBR Q# 2029376 BMT Q# 2028440 | CA
[6 empty] | BD-4130 | BBR-E10596 122019 and NMA464 Endorsements updates | Story | UAT | BBR Q# 2029387(NY) | NY
Stories | [5 empty] | BD-7206 | GC BOR Won't Process | Bug | UAT | WG00003885AA
# | ID (BD-) |  | Test Cases
| 7230 | API
| 7228 | API
| 7229 | API
| 7756 | API
| 7205 | BMT/BBR | x-3 |  | This is related to BD-7879 (Blocker)
| 4130 | BBR | x
| 7379 | BMT
Blockers or Importatnt tickets for the release
Notes:
We did not go on production due to two blockers. Moved from June 24th to July 1st
BD-7942 | is an API blocker
BD-7879 | UAT | Esta Relacionado con BD-7205
BD-8030 | UAT/efix | Verified and it is ok in both envirnonments, getting the expected result.
BD-8082