## November 2022
UAT Releases
Release Date | # of Releases | # of US Tested | # of Defects Tested | # Test Cases Created | Comments
2022-11-04 | 0 |  |  |  | Sprint 3 + Sprint 4 - Cancelled
2022-11-11 | 1 | 10 | 3 | 30 | Sprint 5
2022-11-23 | 1 | 12 | 1 | 15 | Sprint 6
2022-11-28 | 1 | 1 | 0 | 13 | Sprint 7
Totals | 3 | 23 | 4 | 58
UAT Raised Defects
ID | Severity | Priority
BD-13657 | Mayor | Mayor
BD-14619 | Medium | Medium
Weekly Notes:
From: | To:

## October 2022
UAT Releases
Release Date | # of Releases | # of US Tested | # of Defects Tested | # Test Cases Created | Comments
2022-10-07 | 1 | 5 | 0 | 11
2022-10-14 | 1 | 2 | 0 | 6
2022-10-21 | 1 | 2 | 0 | 5
2022-10-28 |  |  |  |  | Canceled due to an API issue related to BD-11648
Totals | 3 | 9 | 0 | 22
UAT Raised Defects
ID | Severity | Priority
BD-12876 | Medium | Medium
BD-12472 | Medium | Medium
Weekly Notes:
From: | To:

## September 2022
UAT Releases
Release Date | # of Releases | # of US Tested | # of Defects Tested | # Test Cases Created | Comments
2022-09-09 | 1 | 6 | 0 | 25
2022-09-16 | 1 | 2 | 0 | 11
2022-09-29 | 1 | 2 | 0 | 21
Totals | 3 | 10 | 0 | 57